# CONCEPT NOTE

STRENGTHENING VAT COMPLIANCE AND AWARENESS THROUGH FIELD VISITS IN 9 DISTRICTS: ‘’MUHANGA, RUHANGO, HUYE, RUSIZI, NYAMASHEKE, KARONGI, RUBAVU, NYABIHU, AND MUSANZE’’

- Background

The Rwanda Wood Value Chain Association (RWVCA) is committed to strengthening its institutional capacity and improving the quality of services provided to members. As part of this mission, RWVCA organizes field visits to reinforce engagement, provide direct support, and ensure that members benefit from professional guidance.

A similar initiative was successfully conducted in the Eastern Province, specifically in Nyagatare District, where the intervention led to a notable increase in VAT compliance and revenue collection. This positive outcome demonstrated the value of direct engagement with members and the importance of strengthening accountability at the grassroots level. Building on this success, RWVCA now seeks to extend the approach to the Southern, Western, and Northern Provinces. These visits are not only an opportunity to address compliance and financial reporting issues but also a strategic step in institutional strengthening, enabling RWVCA to build trust, enhance transparency, and deliver more effective services across the wood value chain sector.

| - Statement of Issues | VAT compliance and financial records audit. |  |  |  |
| --- | --- | --- | --- | --- |
| - OBJECTIVES | Main Objective: To strengthen RWVCA’s institutional capacity and improve service delivery by engaging members directly through field visits in the Southern, Western, and Northern Provinces, thereby enhancing VAT compliance, accountability, and trust within the wood value chain sector. Specific objectives: - To bring RWVCA closer to its members by providing direct support and improving the quality of services delivered. - To raise awareness among members and timber traders about VAT obligations, invoicing requirements, and penalties for non-compliance. - We will conduct mobilization in ICPCs on key activities being prepared for members, including RPL and Insurance. This will also help us organize a database of those working in the carpentry secto - To reinforce RWVCA’s professional image and accountability through structured field activities and financial oversight. - To review and verify the accounting records maintained by field staff, ensuring that the information presented in their reports is consistent with the entries recorded in the daily financial books. - To build on the positive results achieved in Nyagatare District, where VAT compliance and revenue collection improved significantly, and extend similar benefits to the Southern, Western, and Northern Provinces. - To foster cooperation with RRA and conduct monitoring visits that reinforce compliance, fair competition, and transparency in timber markets. |  |  |  |
| - EXPECTED OUTPUTS | - Increased issuance of valid invoices. - Strengthened RWVCA–RRA collaboration. - Significant growth in VAT revenue collection. - Enhanced trust and accountability in the timber value chain. |  |  |  |
| - Participants AND Site visit | First day | Activity Visiting Business |  | Accommodation venue |
| Participants: - MUKAYISENGA Marie Olga - BIZUMUREMYI Emmanuel - NKOMEZUMUTIMA Jean Claude - MUHIRWA Felecien | May,11,2026 From 9h00’ to 15h30’ | Meet with Business operators in Muhanga, Ruhango, and Huye ICPCs |  | Overnight stay scheduled in Rusizi. |
|  | 2nd DAY/ May 12,2026 From 9h00 to 16h00’ | Meet with Business operators in RUSIZI, NYAMASHEKE And KARONGI ICPCs |  | Overnight stay scheduled in Rubavu |
|  | 3rd Day/ May 13,2026 From 9h00 to 16h00’ | Meet with Business operators in Rubavu, Nyabihu And MUSANZE ICPCs (especially Musanze, we will hold a meeting with timber traders as well as carpenters working in the ICPC.) |  | Return to Kigali |
| - Budget | Team | Period | Premium | Accommodation |
|  | - MUKAYISENGA Marie Olga: HR & Adminstration | 3days and 2nights | 12,000*3= 36000 | 50,000*2=100,000 |
|  | - BIZUMUREMYI Emmanuel: Membership coordinator | 3days and 2nights | 12,000*3=36,000 | 50,000*2=100,000 |
|  | - NKOMEZUMUTIMA Jean Claude: Accountant | 3days and 2nights | 12,000*3=36,000 | 50,000*2=100,000 |
|  | - MUHIRWA Felecien: Driver | 3days and 2nights | 8,000*3= 24,000 | ??? |
|  | S/Total |  | 132,000RWF |  |
|  | Grand Total: Transport: One RWVCA vehicle. |  |  |  |
| - Institutions to be formally notified in writing. | - MUHANGA District: We will inform the RWVCA President at the District level - Ruhango District: We will inform the RWVCA President at the District level and ICPC president. - HUYE District: We will inform the RWVCA President at the District level. - Rusizi District: A formal letter will be addressed to the Rwanda Revenue Authority (RRA), requesting the presence of its District representative in Rusizi to participate in a meeting with timber traders. Then we will give a copy to the District and to the RWVCA President at the District level. - Nyamasheke District: A formal communication will be addressed to the RRA, inform them our staff will be supporting timber traders in issuing invoices for their transactions. Copies with the District administration and the RWVCA President at the District level. - Karongi District: We will inform the RWVCA President at the District level. - Rubavu District: We will inform the RWVCA President at the District level. - NYABIHU District: We will inform the RWVCA dean at Province level and ICPC President. - MUSANZE District: We will inform the RWVCA dean at Province level. |  |  |  |
| - CONCLUSION | This official mission is anticipated to generate meaningful and positive outcomes. It will strengthen institutional collaboration, improve operational efficiency, and enhance the productivity of our daily activities. The visit will leave a lasting impact, ensuring that the results of our work continue to grow and multiply over time. |  |  |  |

Done at Kigali, on May 05, 2026

Prepared by

BIZUMUREMYI Emmanuel

Membership Coordinator

Approved by:

Marthe DUSHIMIRIMANA

Executive Director