## MEMBERSHIP & LOGISTIC
ACTIVITY CODE | PLANNED ACTIVITY |  | DEPARTMENT | REALISATION |  |  | PLANNED BUDGET (RWF) | EXCUTED BUDGET (RWF) | SOURCE OF BUDGET | QUARTER 1 | [11 empty] | QUARTER 2 | [11 empty] | QUARTER 3 | [11 empty] | QUARTER 4
|  | UNPLANNED ACTIVITY |  |  | IMPACT/ OUTCOME | KPI |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUG |  |  |  | SEPT |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC
[10 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | Organizational development
1.1.9 | Organize of elections of RWVCA representatives in districts, provinces and platforms. |  | MC | The elections were done at a rate of 90% | RWVCA is represented at all levels. | ELECTION REPORT |  | 10279750 | bar: JAN W1 to FEB W4
1.1.10 | Organize a first meeting of the small team for preparing the elections. |  | MC | 2meetings done | The elections were conducted in an orderly and successful manner. | meeting resolutions | bar: JAN W1 to FEB W2
1.3 | Membership management mobilisazation (Field visit) |  | MC | we have visited 6 ICPCs( Kirehe,Ngoma,Kayonza,Rwamagana,GAHANGA and GICUMBI) |  | visit report |  | 206000 | bar: FEB W3 to FEB W4
1.3.1 | Membership Mobilization/ 50NEW and 120 renuable . 60 members who had become dormant will be encouraged to return to the Association |  | MC | 32New members joined the Association | Membership has increased, and we are also seeing members from new platforms. | LIST OF MEMBERS | bar: JAN W1 to FEB W4
1.3.2 | Organize 1 meeting of ICPCs president |  | MC
1.3.3 | Negotiation on avail timber collection sites |  | MC | bar: FEB W1 to FEB W4
1.3.4 | Organize a meeting with timber suppliers |  | MC | bar: JAN W4
1.3.5 | Conducting a census of wood value chain operators in Rwanda. |  | MC
1.3.6 | Collaborate with ICRAF to develop the services offer to tree nurseries and forest operators |  | MC
1.3.7 | Indentify and visit potential members |  | MC
1.3.8 | Identification key potential members |  | MC | So far we have identified 3 potential members. |  | Contacts and location | bar: JAN W1 to FEB W4
1.3.9 | Identification of the new zones of timber trade that need to avail the MROs |  | MC
1.4.1 | Ordering office assets (1 laptop for ED's Assistant & Tablet for Ngororero)
1.4.2 | Ordering others kitchen tools and equipments | bar: JAN W1 to JAN W4
1.4.3 | Office decoration (Flowers,...........) |  | MC | We have completed the preparation of the vases for planting flowers |  | The vases are available |  | 33000 | bar: JAN W1 to JAN W4
1.4.4 | Upgrade camera and accessories
1.4.5 | Office stationeries |  |  | We purchased office equipment |  | Delivery note |  | 571500 | bar: JAN W4
1.4.6 | Office chairs, |  |  | We have bought two office chairs |  | purchase order and delivery note |  | 940000 | bar: JAN W3
1.4.7 | Back cover for the car
1.4.8 | Food and Huygens need to be ordered |  |  | It's done | The living conditions of staff are steadily improving, which allows them to carry out their duties with confidence and peace of mind. | delvery note |  | 2924093 | bar: JAN W1 to FEB W4
1.4.9 | Purchase Wall-Mounted Projection Screen
1.4.10 | To find a fuel station where the vehicles will refuel. |  | Logistic | We have found a fuel station to work with. |  | MoU |  | 1600000 | bar: JAN W1 to FEB W1